## Cover Page
Big Data Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2025-06-15
Project Team Name |  | Group 01
Project Topic |  | Hands-On Real Time PySpark Project for Beginners - NYC Taxi Data Analysis
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[8 empty] | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20
1. Project Kick-off & Detailed Planning |  |  | 2025-06-09 | 2025-06-10 | All |  | Done
| 1.1 Review Project Guide & Define Scope |  | 2025-06-09 | 2025-06-09 | Kien Hung |  | Done | bar: 2025-06-09
| 1.2 Formalize Roles & Responsibilities |  | 2025-06-09 | 2025-06-09 | Quang Duy |  | Done | bar: 2025-06-09
| 1.3. Set up Project Structure (Folders & Git) |  | 2025-06-10 | 2025-06-10
2. Environment Setup & Data Acquisition |  |  | 2025-06-10 | 2025-06-12 | All |  | Done
| 2.1. Install Required Libraries (requirements.txt) |  | 2025-06-10 | 2025-06-10 | All |  | Done | bar: 2025-06-09
| 2.2. Install & Configure PySpark |  | 2025-06-11 | 2025-06-11 | All |  | Done | bar: 2025-06-10
| 2.3. Download Sample Dataset (NYC Taxi Parquet) |  | 2025-06-12 | 2025-06-12
3. Initial Data Exploration (EDA) |  |  | 2025-06-12 | 2025-06-13
| 3.1. Create Data Exploration Notebook |  | 2025-06-12 | 2025-06-12 | All | Screenshot of working environment | Done | bar: 2025-06-10 to 2025-06-12
| 3.2. Load Data & Analyze Schema |  | 2025-06-13 | 2025-06-13 | All | Dataset files available locally | Done | bar: 2025-06-12
| 3.3. Perform Basic Statistical Summary |  | 2025-06-13 | 2025-06-13 | All | Successful run of a simple script | Done | bar: 2025-06-13
4. Week 1 Reporting & Final Check |  |  | 2025-06-14 | 2025-06-14
| 4.1. Compile Weekly Progress Report (.docx) |  | 2025-06-14 | 2025-06-14 | Kien Hung | Week1_Report.docx file | In-progress | bar: 2025-06-13
| 4.2. Design Weekly Progress Slides (.pptx) |  | 2025-06-14 | 2025-06-14 | Quang Duy | Week1_Presentation.pptx file | In-progress | bar: 2025-06-13
| 4.3. Final Team Review & Submit |  | 2025-06-14 | 2025-06-14 | All | Submitted report and slides | In-progress | bar: 2025-06-13
WEEK 02
1. Bronze Layer Implementation |  |  | 2025-06-16 | 2025-06-16
| 1.1. Develop Bronze Layer Script (bronze_layer.py) |  | 2025-06-16 | 2025-06-16 | Quang Duy | bronze_layer.py script completed and pushed to Git | In-progress | bar: 2025-06-16
| 1.2. Run & Validate Bronze Layer Output |  | 2025-06-16 | 2025-06-16 | All | Delta table created successfully in data/bronze/ | In-progress | bar: 2025-06-16
2. Silver Layer Implementation |  |  | 2025-06-17 | 2025-06-18
| 2.1. Develop Silver Layer Script (silver_layer.py) |  | 2025-06-17 | 2025-06-17 | Kien Hung | silver_layer.py script for cleaning & validation | In-progress | bar: 2025-06-17
| 2.2. Implement Feature Engineering Logic |  | 2025-06-18 | 2025-06-18 | All | Code to create new columns (trip_duration, speed_mph, etc.) added | In-progress | bar: 2025-06-18
| 2.3. Run & Validate Silver Layer Output |  | 2025-06-18 | 2025-06-18 | All | Delta table created successfully in data/silver/ | In-progress | bar: 2025-06-18
3. Gold Layer Implementation |  |  | 2025-06-19 | 2025-06-20
| 3.1. Design Business Aggregations |  | 2025-06-19 | 2025-06-19 | All | Agreed list of aggregations for Gold Layer (e.g., hourly stats, location stats) | In-progress | bar: 2025-06-19
| 3.2. Develop Gold Layer Script (gold_layer.py) |  | 2025-06-19 | 2025-06-20 | Quang Duy | gold_layer.py script to create aggregated tables | In-progress | bar: 2025-06-19 to 2025-06-20
| 3.3. Run & Validate Gold Layer Output |  | 2025-06-20 | 2025-06-20 | All | Multiple aggregated Delta tables created in data/gold/ | In-progress | bar: 2025-06-20
4. Week 2 Reporting & Final Check |  |  | 2025-06-21 | 2025-06-21
| 4.1. Compile Weekly Progress Report (.docx) |  | 2025-06-21 | 2025-06-21 | Kien Hung | Week2_Report.docx with code snippets and results | In-progress
| 4.2. Design Weekly Progress Slides (.pptx) |  | 2025-06-21 | 2025-06-21 | Quang Duy | Week2_Presentation.pptx showing the Medallion flow | In-progress
| 4.3. Final Team Review & Submit |  | 2025-06-21 | 2025-06-21 | All | Submitted report and slides | In-progress